## SW Release Checklist
Software Release Checklist - PSF
Checkpoint | Response | More information
Software Component name | FW Stack
Release Version | V0.90
Release date | 2019-10-24
Is the deliverable / package uploaded in version control system ? Provide the path to the same. | Yes | //depot_dsg/PSF/Release/V0.90/
Is there a software release note associated with this release ? Provide the path to the same in Version Control system | Yes | //depot_dsg/PSF/Release/V0.90/PSF Software Release notes.docx
Is there a software test report associated with this release ? Provide the path to the same in Version control system | Yes | //depot_dsg/PSF/Testing/v0.90/PSF_Developer_Test_Report_V0.90.xlsm
Have you archived all the test logs as applicable ? Provide the path to the same in Version control system | Yes | //depot_dsg/PSF/Testing/v0.90/logs
Does the release notes clearly identify the type of release as one of Alpha / beta / production release candidate? | Yes | Web release
If the release type is alpha / beta release, Does the release notes capture the list of requirements that're not implemented / limited functionality? | Yes
If there're new features added in this release, Is it ensured that the following are revised? 1. Software requirements specification (SRS) 2. Software Design document (SDD) 3. Software Developer test plan (SDTP) 4. Software requirements tracker (SRT) | Yes | //depot_dsg/PSF/Project_Management/Design/
Have all the code changes been commented appropriately (Including Bug#)? | Yes
Have you run PCLint (or any similar static verifiers) to identify & fix potential errors in the source code ? | Yes
Is the version number unique (That is no earlier version exists with the same version number) ? | Yes
In case of applications, Is the version number updated in File version, Product version & GUI About box uniformly ? | Not Applicable
If the deliverable does not have a version resource (firmware for example), does the file name of the deliverable include the version number ? | Yes
Has the source code been updated & labelled in version control system in the format Projectname_ComponentName_Vx.yy ? | Yes | //depot_dsg/PSF/PSF/ & PSF_STACK_V0.90
Was the labelled source code retrieved from Version control system & deliverables built match the release deliverables ? Also name the person who did this cross check | Yes | Poornima
Is the user guide / help file updated including screenshots, if any ? | No | User guide not planned this part of release
If the deliverable is a firmware for Hub products, Have you ensured that all unused locations are set to 0xFF & NOT to any other value (like 0x00 or 0x5A, etc) ? | Not Applicable | NA
THIS DOCUMENT IS UNCONTROLLED UNLESS OTHERWISE STAMPED. It is the user’s responsibility to ensure this is the latest revision prior to using or referencing this document. | Page | Form No. | Rev.
© Microchip Technology Inc. | 1 of 1 | FRM-50381-002 | A